## USAFA Workshop

## Operations and Logistics

Checklist

- Facility: Can hold 50+ people and has access to an area for the CFA (pullup bar and track)

- Schedule Planning meetings and/or concalls: Use freeconferencecall.com

- Invitations and RSVPs: Invite any student 6th grade and older. Focus on 10th and 11th grade. Require an RSVP to keep commitment to attend

- Create Attendee Handout/Packet

- Checkin Table and Packet Handout: for students only

- Food and Beverages: water and snacks; paid by ALOs and Parents Club

- Program

USAFA Speakers: Selections, Counselors, Div Lt’s, RD

Congressional offices

ROTC rep

DV's (short welcome speaker)

Agenda and Briefings - Coordinate with USAFA staff.

- CFA: Ensure adequate time, people, instructions

- 1:1 Assessments: VERY important to get this right. Tailored advice for each attendee (academics, fitness, leadership/character)

- Lt’s for Q&A – Remind Lt’s this is for prospective applicants

- After-event dinner: for ALOs and staff only; not applicants; review feedback

- After Action Report / Lessons Learned meeting

- Continuity Folder: for next year

## USAFA Workshop

## <AREA>

## <DATE>

## Operations and Logistics 
Plan

### Schedule of Planning meetings

<Pre-plan and schedule approximately 6 calls.  2 days prior, weekly for the 3 weeks prior, bi-weekly 2 months prior>

Conference Dial-in Number and Code:

### Facilities

ALO:

Location can hold 50+ people; and has access to an area for the CFA (pullup bar and track)

Contact info

Room setup instructions

### Security and Parking

ALO:

Requirements, Logistics

Contact info

### Invitations and RSVPs

ALO:

Invitations sent via online tool

Tailored invitation letters depending on status

Include Instructions to students of what to bring: sample resume, gym clothes

Use summer seminar applicant list

Get Pre-Junior database from Admissions for invites.

ALOs can provide lists of students if they are not in USAFA databases.

Followup from ALOs really helps – both summer seminar and applicants.

Create short URL for forwarding (tinyurl.com)

Example: http://tinyurl.com/USAFA-LA-2016

Total # of Students

Total # of Guests

Total # of Influencers

Total # of ALOs

Total # of Registrants

### Attendee Handout/Packet

ALO:

Agenda

USAFA Notepads

USAFA Contact info (websites, phone/email of counselors, etc)

CFA scoresheet

USAFA Application Checklist (printout from ALOWeb candidate application)

ROTC flyer

Feedback – 3 forms for student and parents; Email survey

Nametag

Class profile

CFA test dates (Oct, Nov, Dec, Jan)

Etc.

### Checkin Table and Packet Handout

ALO:

NLT 0700 Arrival and keep attendees outside until we are setup.

Use Table banners

If possible, pickup or pre-position materials, snacks, dring, 1 or 2 days prior.

Station people, balloon or sign, for easel on sidewalk for guiding to GCC.

Place sign outside showing when doors will open (745AM)

Easel, Coolers with Ice, Dolly

Water/Coffee/snacks – parent club.

Bananas, nuts, apples, other healthy snacks

USAFA Marketing giveaways

Parents Club product sales if appropriate

Have backup plan, mobile numbers.

### Food and Beverages

ALO:

Bottled Water.  Smaller 8oz bottles

Possible snacks. Parents Club may support.

String cheese, snack bars, healthy snacks.

Give food court a heads up.  Set expectations for attendees as they go to lunch.  Might be long lines.  Give heads up at 1000.

Bring: Coffee, napkins, small cups, ice chests, power strip, extension cord.

### Program

### USAFA Speakers

LOD

Invites to Selections, Counselors, Div Lt’s, RD

Congressional offices

ROTC rep

### DV's

LOD

Welcome speaker (use helmet, other show/tell items, flight suit)

Invite/notify local commander if appropriate

Congressional Staffer(s)

When needed: Invites, Expectations, Logistics, Suggested topics, confirmation; Guide discussion for speaker; Have 1:1 prior to set the theme.

### Agenda and Briefings

LOD

Coordinate with USAFA staff.

Advise audience upfront: “You may know some/most of this information”

Since workshop: Provide Expectations of Assessment;

Provide Interviewing tips:  Know strength and areas to improve; Bring pen/paper; check email/spam

Parents: practice interviewing, role playing

Practice communications (introduce self, ask Q&A questions); Honor Code; Fitness

Deliver to AV person prior to event.

Keep briefings short. More pictures. Less words. Briefers should modify to suit their style.

Parents briefing and Q&A.  Focus on Preparing for and supporting the Admissions process; Not In-processing, etc.

LOD personally review all briefings

### CFA

ALO:

See separate CFA plan for details

Prob Not Possible for official CFA test

Demonstrate all exercises.  Use a Female officer to demonstrate 3 pullups.

Be strict on the achievement of individual exercises. Proctors need instructions prior.  Possibly keep proctors at stations while students move through-would need more proctors; instead of Proctor guiding the group through the stations. Maintain 5 minute intervals.

Group A (seniors) go through CFA first

Schedule future CFA’s so students can add it to their schedule.

### 1:1 Assessments

LOD

Use Foyer with (8-10) 2x6 foot tables.

Possible Assessors: (Confirm)

*15 minute timeslots

Moderator/time keeper:

Plan on 5 assessments in 2 hours per person.

Training videos online

Prioritize Group A for Seniors

Juniors – if time permits we can do Juniors in Group B – use different color form

Use a dedicated assessor for Juniors, high-competitive, low-competitive

Instructions:

Prior: Student fills in name, ALO, Counselor on Snapshot form.

Moderator will hand Snapshot form / CFA Scoresheet to student.

Student hands Snapshot form with CFA scores, and leadership resume to Assessor.

- Assessor asks questions; and provides verbal and written feedback on Snapshot form and return it to the Student

- Assessor records notes for LOD/ALO;  Assessor keeps resume for the ALO.

- Send instructions 1 week prior to the Assessors

ALO:

Binders for each Assessor:

- Instructions (Objectives and Expectations of Assessors)

- Pool of Standard questions

- Master list of student info and notes back to LOD/ALO

Handout binders to Assessors and brief them ahead of what to do.

Use Table numbers

Encourage parents to take notes but not ask questions

Timers on table; or use phones.

High competitive -

Heli parents -

Low competitive –

Juniors or younger -

### Lt’s for Q&A

ALO:

Open session - no breakouts

Always nice to have more, but 2-3 is sufficient.  If we have enough Lt’s, possibly have 2 sessions simultaneously - students and parents.

Remind them these are parents and prospective candidates. How you feel about your service to the Force. Why it’s different. Why you are proud to serve. What is 1 piece of advice for the application process.

### After-event dinner

LOD

Short ALO Meeting immediately after workshop.

Optional Group dinner to follow

Invite to all ALOs; remind to bring casual clothes; remind of menu and expected cost per person.

### After Action Report / Lessons Learned meeting

LOD

Local review and Hotwash

Copy to USAFA Admissions

Consolidate feedback from online survey.

### Continuity Folder

LOD

Copy to USAFA Admissions

Correlate attendance to completed application or offers.

### Agenda

0800 – Introductions (LOD)

0810 - Welcoming Remarks (Special Guest)

0825 – Greeting (Congressional; optional)

0830 - USAFA Review

0900 - USAFA Admissions - "Putting Your Package Together”

- USAFA Selections - "How We Compose a Class"

1000 - Candidate Fitness Assessment (CFA) (Students—Gym/Track)

1000 - Parents Briefing (Parents)

1130 – 1230 Group A - Assessments/Networking Q&A
                     Group B - Lunch

12:30 – 1330 Group A - Lunch 
                      Group B - Assessments/Networking

1330 – Workshop on Communications

1345 – Association of Graduates

1400 - Congressional Nominations

1430 - Alternative Paths to the Air Force

1440 - The ALO Interview - "Telling Your Story"

1500 - Q/A with Recent USAFA Graduates

1530 - Wrap Up and Adjourn